## Website Development
| Calculated Total Time Estimate in hours | 587
| Cost Estimate | 8805
A = Analysis ¦ D = Design ¦ C = Coding ¦ Q = QA ¦ M = Management
Sr.No. | Functionality | Total Hrs | A | D | C | Q | M
| Analysis | 35 | 35
| Creative Design | 48 |  | 48
| HTML (Responsive) | 42 |  | 42
| QA | 40 |  |  |  | 40
| Management | 20 |  |  |  |  | 20
With Ref. to SOW | Website Basics
2.3.1 | Navigation | 12 |  |  | 12
2.3.1.1 | Header | 0
2.3.1.2 | Navigation Bar | 0
2.3.1.3 | Footer | 0
2.3.2 | Home Page | 24 |  |  | 24
2.3.2.1 | Search | 12 |  |  | 12
2.3.2.1.1 | Search Detail Page | 18 |  |  | 18
2.3.3 | Activities | 16 |  |  | 16
2.3.3.1 | Activity Detail Page | 16 |  |  | 16
2.3.3.1.1 | Book Now | 60 |  |  | 60
2.3.3.1.1.1 | Booking Page | 0
2.3.3.1.1.2 | Cancellation Policy | 0
2.3.4 | Escrow System | 32 |  |  | 32
2.3.5 | Registered User (EventSpace Owners) Section | 0 |  |  | 32
2.3.5.1 | Registration | 32
2.3.5.2 | Dashboard | 0
2.3.4.2.1 | Profile | 0
2.3.4.2.2 | Location Details | 0
2.3.4.2.3 | Reviews and Ratings | 0
2.3.4.2.4 | Payments | 0
2.3.4.2.5 | Add Space | 24 |  |  | 24
2.3.4.2.6 | Answer Questions from the interested guests | 8 |  |  | 8
2.3.6 | Commissions | 18 |  |  | 18
2.3.7 | User (Guest) Section | 40 |  |  | 40
2.3.7.1 | Login | 0
2.3.7.2 | Register | 0
2.3.7.3 | Browse Eventspaces | 0
2.3.7.4 | Reviews and Ratings | 0
2.3.7.5 | View Owner’s Profile | 0
2.3.7.6 | Message Owners | 0
2.3.7.7 | View Payment History | 0
2.3.7.8 | Cancellation and Refunds | 0
2.3.8 | About Us | 2 |  |  | 2
2.3.9 | Blog | 2 |  |  | 2
2.3.10 | FAQ’s | 2 |  |  | 2
2.3.11 | Contact Us | 2 |  |  | 2
2.3.12 | Emails and Notifications | 4 |  |  | 4
2.3.13 | Dispute Management | 8 |  |  | 8
2.3.14 | Admin Section (Web-based) | 70 |  |  | 70
2.3.14.1 | Login | 0
2.3.14.2 | Manage Static Pages | 0
2.3.14.3 | Manage Images | 0
2.3.14.4 | Manage Users | 0
2.3.14.5 | Manage Activities/Event Categories | 0
2.3.14.6 | Manage Reviews and Ratings | 0
2.3.14.7 | Manage Disputes | 0
2.3.14.8 | Access reports | 0
2.3.14.9 | Commission | 0
2.3.14.10 | Manage FAQs | 0
2.3.14.11 | Manage Blog | 0
2.3.14.12 | Manage Contact Us Messages | 0
2.3.14.13 | Manage Notifications | 0
2.3.14.14 | Messaging | 0
| Total | 587